## Sheet1
		PROJECT PLAN – WHEN FISH GO HOME

	NỘI DUNG	THÁNG 7					THÁNG 8
	THỜI GIAN	20 – 24		27 – 31				3		4		5		6		7		10		11		12		13	14	17	18	19	20	21	24	25	26	27	28	31
WHEN FISH GO HOME	Xây dựng ý tưởng	Cả Team

	Render 3D cơ bản	NGUYỄN TRẦN VĨNH THUYÊN – ĐỖ THÀNH NAM
	Xây dựng Game Structure Architecture	NGUYỄN TRẦN VĨNH THUYÊN – ĐỖ THÀNH NAM
	Resource 2D và 3D			NGUYỄN TOÀN THẮNG – ĐOÀN VIỆT HÙNG
	Xây dựng Map						NAM – THUYÊN
	Xây dựng thuật toán tìm đường (JPS)						NAM
	Xây dựng AI						NAM – THUYÊN
	Xây dựng bộ điều khiển Game.						THUYÊN
	Collision Detection và Ray Casting						NAM – THUYÊN
	Render Menu Game						NAM – THUYÊN
	Xử lý Item						NAM
	Port Android						THUYÊN
	Fix Bug, Leak Memory	THUYÊN – NAM
	Tối ưu hóa Game.	THUYÊN – NAM
	Báo cáo và thuyết trình						CẢ TEAM

## Compatibility Report
Compatibility Report for KeHoachCongViec.xls
Run on 7/17/2013 22:28

The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.

Minor loss of fidelity			# of occurrences	Version

Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available.			5	Excel 97-2003